## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-TAsgxPlSUCBv7DeVudijckAHH2S | Define objectives and design component diagram for post-harvest quality monitoring | Objectives & Methodology | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-08-10 | 08/25/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Define the task scope, expected outputs, and component-level design for the assigned SMARTCINNAMON module.
1XkqkERZlEy9HYk3ux04YskAEIfC | Write final combined research problem | Research Gap & Problem | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-08-30 | 09/06/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Analyze existing limitations and clearly define the research gap addressed by the SMARTCINNAMON project or assigned component.
3SLwxzqtUEewIB_nAmv6YskAEPBV | Internal TAF Review | Topic Planning & TAF | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-06-10 | 06/25/2025 | false | false | 03/08/2026 | RANDENI R.P.R.M it22578778 |  |  |  | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
53F-9jFlDkiamc1C_r33jckADZJC | Develop a monitoring model for warehouse quality assessment and risk detection. | Model / System Development | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-12-15 | 01/01/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Develop and test the required model according to the planned architecture, dataset, and project objectives.
7Ng4AV3M4kOKlziM3U60wMkAMVx6 | Prepare TAF Document | Topic Planning & TAF | Completed | Important | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-04-14 | 05/05/2025 | false | false | 03/08/2026 | RANDENI R.P.R.M it22578778 |  |  |  | Complete the Topic Assessment Form with project title, problem background, objectives, novelty, and team member details.
FA8-FVYIK0WG02-NF9Ed0ckANyrE | Identify multi-parameter system requirements and architecture design for warehouse monitoring. | Requirements & Architecture | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-08-20 | 09/10/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Identify functional and technical requirements, then prepare the architecture design needed for implementation.
Mhl9LQTOE06ITW8jydMhW8kACqDL | Collect papers for IoT in cinnamon | Literature Review | Completed | Medium | VIHANI W.W.G.D it22594372;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-06-19 | 07/10/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
QpChDChqOU2ZK_QLmvbT_8kAOrqg | Collect papers for ML in cinnamon | Literature Review | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-06-19 | 07/10/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
TyH1WmmzqUubdVRO082Xi8kAIWUv | Finalize research topic and supervisor.co supervosor | Topic Planning & TAF | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-05-05 | 05/26/2025 | false | false | 03/07/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Finalize the research area, identify the supervisor and co-supervisor, and get initial approval for the selected topic.
X7n1bSsQ9kKS8tayhOLCD8kAMYyH | TAF assesment by supervisor and co supervisor | Topic Planning & TAF | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-06-26 | 07/17/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
ilVYTJZOREmKy828OHUA1MkADUuV | Design system overview diagram | Objectives & Methodology | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-08-12 | 09/02/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Define the task scope, expected outputs, and component-level design for the assigned SMARTCINNAMON module.
itHSNVmUCEaPZKV_kJ59EckAFM_T | Define Agile SDLC methodology for SMARTCINNAMON | Objectives & Methodology | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-09-09 | 09/30/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Complete the planned Objectives & Methodology task for the SMARTCINNAMON research project, ensuring accuracy, evidence, and timely progress.
pq6z-zhkSkGu9X9x1RCeHckAMMiY | Identify gap in post-harvest quality monitoring | Research Gap & Problem | Completed | Medium | VIHANI W.W.G.D it22594372 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-08-16 | 09/06/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Analyze existing limitations and clearly define the research gap addressed by the SMARTCINNAMON project or assigned component.
qiJI3G1KtEWjGMD1OF4agMkALKdX | Prepare environmental sensor datasets including humidity, temperature, and gas levels for monitoring. | Data Collection / Dataset Preparation | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-10-11 | 11/01/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Gather, organize, and prepare the required dataset for analysis, model development, and validation.
yFEmDZ7wl0q5hUjnMK4sDckAON6v | Collect papers for smart cinnamon | Literature Review | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-06-16 | 07/07/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
0r4Usr8iBE-YV5KEN1-B7MkADM5m | Submit research publication evidence | Final Submission | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-05-09 | 05/30/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372
wvXb-NgnC0GpseTsRxBWsskAB82s | Submit research paper | Final Submission | Completed | Medium | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-13 | 05/04/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372
yQchjHVMR0e7wNisfNhpjskAJIXT | Submit final checklist | Final Submission | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-09 | 04/30/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372
oKcYhqvnHU-91QuiA_dZ7skAO_Su | Submit logbook | Final Submission | Completed | Medium | BANGAMUWAGE.M.D it22592606;RANDENI R.P.R.M it22578778;HANSAJITH W.R.N it22565594;VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-27 | 04/30/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372
ZW45Exllu0ORCEghPDuk2MkAOqHR | Prepare and submit final report | Documentation | Not started | Important | RANDENI R.P.R.M it22578778 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-22 | 05/13/2026 | false | false
XgIko8Zit0CDYeEMgy9Y38kAMXOK | Prepare and submit project website | Final Submission | Completed | Medium | HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-05 | 04/26/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372
V3H2as8adkSGMw-UkwOZ9ckAIwLK | Prepare and submit final presentation and system demonstration | Presentation Preparation | Not started | Important | BANGAMUWAGE.M.D it22592606;RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-04-14 | 05/05/2026 | false | false | 04/30/2026
ovywm9bqIECwFhASaegqSMkANFhm | Conduct final system testing and validation | Testing & Validation | Completed | Important |  | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-03-30 | 04/20/2026 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606
zw_olPY1SUeDmc299JO0OckAKSOf | Prepare and submit individual proposal report | Documentation | Completed | Important | BANGAMUWAGE.M.D it22592606;RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2025-08-29 | 09/19/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Prepare the required academic documentation with final content, formatting, references, and supporting evidence.
8Ml4ilD6C0CMowUljRaIM8kAITx8 | Prepare and submit Progress Presentation 2 (PP2) | Presentation Preparation | Completed | Important | VIHANI W.W.G.D it22594372 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2026-02-17 | 03/10/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Prepare presentation slides, system demonstration flow, and explanation notes for the scheduled evaluation.
0D-46V8gCE2R4IZ1ukrpvskADyvh | Prepare and submit Progress Presentation 1 (PP1) | Presentation Preparation | Completed | Important | RANDENI R.P.R.M it22578778;BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2025-12-18 | 01/08/2026 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  |  | Prepare presentation slides, system demonstration flow, and explanation notes for the scheduled evaluation.
jtJpSo1jkk6-GQgIr-yLh8kAFJdC | Prepare and submit proposal presentation of SMARTCINNAMON system | Presentation Preparation | Completed | Medium | HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/26/2026 | 2025-08-18 | 09/08/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  |  | Prepare presentation slides, system demonstration flow, and explanation notes for the scheduled evaluation.
fS-nb5viR0KAO8bRtzqGV8kAKOqw | System testing and model validation using performance metrics | Testing & Validation | Completed | Medium |  | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2026-02-14 | 03/07/2026 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  |  | Develop and test the required model according to the planned architecture, dataset, and project objectives.
73E7ZDwXTUOxklA5ANj868kAFFlI | Integrated SMARTCINNAMON system development and module integration | Integration | Completed | Medium | BANGAMUWAGE.M.D it22592606;RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2026-02-12 | 03/05/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Combine the SMARTCINNAMON modules, verify data flow, and resolve integration issues before final testing.
lOBg0-BLOkiQYf1RUjuZuckAIH4w | Develop a predictive model for land analysis and vacant area identification. | Model / System Development | Completed | Medium | HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-12-11 | 01/01/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Develop and test the required model according to the planned architecture, dataset, and project objectives.
QD9R_zCKi0S4dEFfokuSH8kAO5zR | Develop a machine learning model for fungal detection and prediction. | Model / System Development | Completed | Medium | RANDENI R.P.R.M it22578778 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-12-11 | 01/01/2026 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Develop and test the required model according to the planned architecture, dataset, and project objectives.
kWwy7dZDkUGcXwiewDzRMckANxBt | Develop a model for soil nutrient monitoring and fertilizer recommendation. | Model / System Development | Completed | Medium | BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-12-11 | 01/01/2026 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Develop and test the required model according to the planned architecture, dataset, and project objectives.
FLdHAR-ghkOESPNJFoqyW8kALBTA | Prepare satellite and drone imagery along with GIS datasets for plantation analysis. | Data Collection / Dataset Preparation | Completed | Medium | HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-10-11 | 11/01/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Gather, organize, and prepare the required dataset for analysis, model development, and validation.
n08XEExfnEyjbjBa1qwOoskAOm5V | Prepare cinnamon leaf image datasets through collection and preprocessing for fungal detection. | Data Collection / Dataset Preparation | Completed | Medium | RANDENI R.P.R.M it22578778 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-10-11 | 11/01/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Gather, organize, and prepare the required dataset for analysis, model development, and validation.
Q2OdstprmkaE9nEX57nSJckAHOlO | Prepare soil sensor datasets including NPK, moisture, and temperature values for analysis. | Data Collection / Dataset Preparation | Completed | Medium | BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-10-11 | 11/01/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Gather, organize, and prepare the required dataset for analysis, model development, and validation.
CfspMRqgwEmLpTQz4BrXcskAHSTy | Identify GIS-based system requirements and architecture design for vacant area detection. | Requirements & Architecture | Completed | Medium | HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-08-20 | 09/10/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Identify functional and technical requirements, then prepare the architecture design needed for implementation.
8LrblJEGb0WjYrmup2adXckAMRMp | Identify system requirements and architecture design for fungal detection and LSTM based prediction. | Requirements & Architecture | Completed | Medium | RANDENI R.P.R.M it22578778 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-08-20 | 09/10/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Identify functional and technical requirements, then prepare the architecture design needed for implementation.
a6G-ovfhSke7IyuLaCATW8kACsRf | Identify IoT-based system requirements and architecture design for soil nutrient monitoring. | Requirements & Architecture | Completed | Medium | BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/23/2026 | 2025-08-20 | 09/10/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Identify functional and technical requirements, then prepare the architecture design needed for implementation.
X_2_ObpIl0aCNxmI3ZDcFckAF8IW | Define objectives and design component diagram for vacant area detection and yield forecasting | Objectives & Methodology | Completed | Medium | HANSAJITH W.R.N it22565594 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-08-04 | 08/25/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Define the task scope, expected outputs, and component-level design for the assigned SMARTCINNAMON module.
yiqW6TMwhUe1w9FxFcNjMskAApz1 | Define objectives and design component diagram for soil nutrient management | Objectives & Methodology | Completed | Medium | BANGAMUWAGE.M.D it22592606 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-08-04 | 08/25/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Define the task scope, expected outputs, and component-level design for the assigned SMARTCINNAMON module.
YWmy924OoE6AqrFeJ2U0ickAF8hC | Define objectives and design component diagram for fungal spread predictor | Objectives & Methodology | Completed | Medium | RANDENI R.P.R.M it22578778 | RANDENI R.P.R.M it22578778 | 03/13/2026 | 2025-08-04 | 08/25/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Define the task scope, expected outputs, and component-level design for the assigned SMARTCINNAMON module.
5mdMuklvTEuZkHWyuCv8UMkAMNMg | Identify gap in vacant area detection and yield forecasting | Research Gap & Problem | Completed | Medium | HANSAJITH W.R.N it22565594 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-08-16 | 09/06/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Analyze existing limitations and clearly define the research gap addressed by the SMARTCINNAMON project or assigned component.
Pj5zRbrRHUK1HQg2l6gKIckAAq5I | Identify gap in fungal progression prediction | Research Gap & Problem | Completed | Medium | RANDENI R.P.R.M it22578778 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-08-16 | 09/06/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Analyze existing limitations and clearly define the research gap addressed by the SMARTCINNAMON project or assigned component.
TBJchxNie02SFlL-S9BATskAKW1f | Identify gap in soil nutrient management | Research Gap & Problem | Completed | Medium | BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-08-16 | 09/06/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Analyze existing limitations and clearly define the research gap addressed by the SMARTCINNAMON project or assigned component.
aKWTHq9Qg0aGpY1wmrdCH8kADCKe | GIS, segmentation, yield forecasting literature review | Literature Review | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-07-18 | 08/08/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
7MaNYd3unEaCeV63px40-ckAGSIW | Fungal prediction and LSTM/GRU literature review | Literature Review | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-07-18 | 08/08/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
Yn3bYW_Ez0W7Bemyn1cpy8kANDQv | Soil nutrient recommendation literature review | Literature Review | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-07-18 | 08/08/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
sKFsZqJU9UWslm60gN2rZskAPgl- | re submit TAF and all changes components | Topic Planning & TAF | Completed | Urgent | BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-10-19 | 11/09/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
58FQ-PxAA0ShvEHhvV54wckAJCz- | Prepare the TAF document individual component | Topic Planning & TAF | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-05-17 | 06/07/2025 | false | false | 04/30/2026 | RANDENI R.P.R.M it22578778 |  |  | Cinnamon leaf fungal spread predictor | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
IZkc1GMnHEuNm2NE_WOnZ8kANw5R | Prepare the TAF document individual component | Topic Planning & TAF | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-05-17 | 06/07/2025 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  | Vacant area detection + yield forecasting | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
XlK19uJk_k-28CDiSzdrAMkAJ0vj | Prepare the TAF document individual component | Topic Planning & TAF | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-05-17 | 06/07/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
tvBM8PRG_0uMx7YwFoG1-ckAEyu2 | Submit TAF | Topic Planning & TAF | Completed | Medium | BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-06-06 | 06/27/2025 | false | false | 04/30/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Submit the final TAF before midnight. Make sure all details are accurate and complete.
sYya94Ehu0iwYbT64Of5DMkABz4z | Post-harvest environmental monitoring literature review | Literature Review | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-11-28 | 12/19/2025 | false | false | 03/08/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
DFwVD-XJK0K1kSJfgXthhskAA31R | Collect papers for cinnamon-specific studies | Literature Review | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/08/2026 | 2025-11-19 | 12/10/2025 | false | false | 03/08/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Collect and review relevant research papers to support the selected methodology, technology choices, and project background.
q3wmJ3cACky3dVUxKaoD68kAHxdG | Prepare the TAF document individual component | Topic Planning & TAF | Completed | Medium |  | VIHANI W.W.G.D it22594372 | 03/07/2026 | 2025-05-17 | 06/07/2025 | false | false | 03/07/2026 | VIHANI W.W.G.D it22594372 |  |  | Post-harvest warehouse quality guard | Prepare, review, and submit the TAF content with required project details, supervisor feedback, and individual component updates.
nBaymOm940uKWb0M20IHy8kAMxIu | Confirm project group and specialization | Topic Planning & TAF | Completed | Urgent |  | BANGAMUWAGE.M.D it22592606 | 03/06/2026 | 2025-05-07 | 06/30/2025 | false | false | 03/06/2026 | BANGAMUWAGE.M.D it22592606 |  |  | Soil nutrient monitoring + fertilizer recommendation system | Confirm the project direction, team roles, supervisor guidance, and specialization alignment for SMARTCINNAMON.
xA_frxyvVU26fNJUa47Zd8kAJ8GZ | Prepare and submit final individual reports | Documentation | Not started | Important | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 04/30/2026 | 2026-04-21 | 05/12/2026 | false | false | [5 empty] | Prepare the required academic documentation with final content, formatting, references, and supporting evidence.
K3gjcTY96E2eSFp3tr-H7ckAJLrN | Prepare final individual draft | Documentation | Completed | Medium | RANDENI R.P.R.M it22578778;VIHANI W.W.G.D it22594372;HANSAJITH W.R.N it22565594;BANGAMUWAGE.M.D it22592606 | VIHANI W.W.G.D it22594372 | 04/30/2026 | 2026-04-07 | 04/28/2026 | false | false | 04/30/2026 | VIHANI W.W.G.D it22594372 |  |  |  | Prepare the required academic documentation with final content, formatting, references, and supporting evidence.

## Plan name
Plan name | SMARTCINNAMON Research Project Planner
Plan ID | qwADxLeGkkCxczo-EYwVcckAGm2j
Date of export | 04/30/2026

## Summary
SMARTCINNAMON Research Project Planner Summary | SMARTCINNAMON Research Project Planner Summary | SMARTCINNAMON Research Project Planner Summary | SMARTCINNAMON Research Project Planner Summary | SMARTCINNAMON Research Project Planner Summary
Metric | Value |  | Bucket Name | Task Count
Total Tasks | 58 |  | Objectives & Methodology | 6
Completed Tasks | 55 |  | Research Gap & Problem | 5
Not Started Tasks | 3 |  | Topic Planning & TAF | 11
Important Tasks | 8 |  | Model / System Development | 4
Urgent Tasks | 2 |  | Requirements & Architecture | 4
|  |  | Literature Review | 8
|  |  | Data Collection / Dataset Preparation | 4
|  |  | Final Submission | 5
|  |  | Documentation | 4
|  |  | Presentation Preparation | 4
|  |  | Testing & Validation | 2
|  |  | Integration | 1